## 2014 3YWP Draft
Three-Year Watershed Implementation Priorities for Hood Canal Coordinating Council
Domain Priority (species benefitting)
Costs are from Recovery Plan estimates and comparables methods and are for plannng purposes only | [5 empty] | 1 | Domain 1 represents natal freshwater and sub-estuarine habitats for 8 extant summer chum subpopulations, 2 extant chinook populations, and 1 extant bull trout subpopulation in the HCCC area. | [9 empty] | Domain 1 represents natal freshwater and sub-estuarine habitats for 7 extant summer chum subpopulations, 2 extant chinook populations, and 1 extant bull trout subpopulation in the HCCC LE area.
Prioritization to be determined by Lead Entity Committees, regional participants, and governments | [5 empty] | 2 | Domain 2 represents natal freshwater and sub-estuarine habitats for 3 re-introduced extinct summer chum subpopulations and all significant nearshore habitats in the HCCC area. | [9 empty] | Domain 2 represents natal freshwater and sub-estuarine habitats for 3 re-introduced extinct summer chum subpopulations and all significant nearshore habitats in the HCCC LE area.
Annual costs represent money obtained and/or spent during calendar year | [5 empty] | 3 | Domain 3 represents natal freshwater and sub-estuarine habitats for all remaining extinct summer chum and chinook subpopulations in the HCCC area. | [9 empty] | Domain 3 represents natal freshwater and sub-estuarine habitats for all remaining extinct summer chum subpopulations in the HCCC LE area.
Projects represent all 4 priority Domains to allow more comprehensive tracking of salmon recovery while supporting community values. | [5 empty] | 4 | Domain 4 represents all other habitats including nearshore areas not labeled as significant. | [9 empty] | Domain 4 represents all other habitats including nearshore areas not labeled as significant.
[7 empty] | 2007 |  | 2008 |  | 2009 |  | 2010 |  | 2011 |  | 2014 |  | 2015 |  | 2016 |  | 2017
Domain Priority (species benefitting) |  | Likely sponsor | Total cost | Unfunded Portion | Existing Funding | Source of other funds | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Scope | Cost | Restor-ation Type | Location w/in watershed | Performance | Brief Description | Relevant Strategy | Action # | Bio Rank / EDT | Primary Limiting Factors | HWS link | HWS link Cont. | 3 YWP Project Name
CAPITAL PROJECTS | [28 empty] | df
Habitat Capital Projects
Mid-Hood Canal (Dosewallips, Duckabush, Hamma Hamma)
1 | USFS/Upper Dosewallips wood-riparian restoration | WFC, USFS, Tribes | 620000 | 620000 | 0 | PSP, USFS, SRFB, PSC | Funding Strategy; Coordination |  | Feasibility/Design | 100000 | Feasibility/Design cont'd | 100000 | finish design concepts, scope LWD sources; riparian assessment | 19570 | 70% designs and NEPA permitting | 30000 | monitoring (phase 1) | 10000 | Construct ELJS in phase 2 | 600000 | monitoring (phase 2) | 10000 |  |  | I,F,R | Mainstem | 4 miles | Place log jams and increase wood loading by helicopter and/or conventional means in strategic locations, including 6 mile bridge, FS boundary, above Camp Acacia, Case Creek, and road washout |  | 33,34,36, 37,38,40 | 1 of 17 | 1,3 | 04-01-001 |  | USFS/Upper Dosewallips wood-riparian restoration
1 | Powerlines, Lazy C, Southshore riparian-floodplain protection Lower Dosewallips | JLT, State Parks, Jefferson Co, HCCC, TNC | 2141225 | 969152 | 1172073 | Jefferson County, SRFB, PSAR, WWRP, Parks | Begin to implement Dosie Acquisition Phase 2 | 163590 | Begin to implement Mid-HC Dosie Acquisition 2007 | 209000 |  |  | Begin to implement Mid-HC Dosie Acquisition 2009 and State Park Acquisition | 764830 | Community Outreach, Planning and Transactions, inc'g Jupiter Tracts | 390000 | Community Outreach, Planning and Transactions | 741225 | Community Outreach, Planning and Transactions | 1200000 | Community Outreach, Planning and Transactions | 200000 |  |  | AP, R | Mainstem | 400 acres | Protect high quality habitats and purchase impaired habitats for future restoration; includes planning effort |  | 20,25,32 | 4,6,9.5 of 17 | 1,3,5 | 04-02-003, 04-02-005, 04-02-006, 04-02-007 |  | Powerlines, Lazy C,Dosewallips Floodplain Acquisition II
1 | Powerlines Lower Dosewallips wood-riparian restoration | WFC, USFS, Tribes, County | 152000 | 151000 | 1000 | PSP, USFWS | Conifer Plantings | 1000 | Feasibility/Design and Landowner Discussions | some work conducted as part of Upper Dose wood project | more outreach and land transactions | some work conducted as part of other projects | Riparian Assessment and project dev't |  | Planting and Exotic Control; sponsor dev't | ? | Riparian Planting and exotic control | 1000 | Riparian Planting and exotic control | 1000 | ELJ design begins?; Riparian Planting and exotic control | 150000 |  |  | I,F,R | Mainstem | 0.5 miles | Improve instream wood loading rates and riparian conditions in the Powerlines Reach |  | 21,23,24 | 6 of 17 | 1,3 | 04-01-004 |  | Lower Dosewallips Powerline Reach LWD Design & Implementation
1 | Lower Dosewallips floodplain/estuary restoration and Dosewallips Estuary Phase 4 | WFC, Tribes, State Parks | 630000 | 30000 | 600000 | PSP, State Parks, BIA, SRFB, ESRP | Landowner Outreach, plantings, design, and permitting | ? | Reach Assess, construction (remove 500ft RB levee below 101, installed 5 ELJs) | 360775 | Deconstruct RB levee above SR101, cont. reach assessment, Planting 0.5 acre | 300000 | Finish reach assessment; planting and maintenance, Monitoring, $ strategy | 100000 | complete property transaction, install ELJs at estuary | 411000 | RB armor and fill removal below 101; 2000ft | 600000 |  |  | Outyear planning for Brinnon levee and improve Sylopash Slough | 30000 |  |  | I,E,F,R | Estuary, Mainstem | 2000ft | Improve riparian conditions, tidal inundation, and floodplain connection; feasibility study included |  | 3,5,6,7,9,11,16 | 7.5,9.5 of 17 | 1,2,3,5,7 | 04-03-007 |  | Dosewallips Floodplain and Estuary Restoration 2011 Phase 4
1 | USFS road decommission Dosewallips | HCSEG | 845883 |  | 0 | SRFB, PSP | [12 empty] | Restoration | 845883 |  |  |  |  | U | Headwater | 8.4 miles | Decommission high priority roads for aquatic risk or convert them to trails | HC SC Recovery Plan, Ch9, p168-sediment aggradation; p176-Olympic National Forest & State Lands; p186 acquire lands/sediment aggradation; Mid-Hood Canal Results Chain: "Reduce sediment delivery from erosion and mass wasting events of USFS roads"; substrate | 27,28,41 | 10 of 17 | 3,4,5 | 04-06-004 |  | USFS road decommission Dosewallips
1 | Dosewallips Barge Removal & Estuary Restoration, Shoreline Acquisitions | HCSEG | 228093 |  | 0 | SRFB, PSAR, ILF? | [10 empty] | Acquisition and restoration | 228093 | [6 empty] | AR,E | Estuary West | 1.5 acre | Remove barge from mouth of Walker Creek inDosewallips estuary and restore tidal inundation and distributary | HC SC Recovery Plan, Ch9, p185, remove barge at mouth of Walker Creek; Mid-Hood Canal Results Chain: "Restore Estuarine Habitat" | 13 | 13 of 17 | 1,2,3,7 | 04-03-006 |  | Dosewallips Estuary Barge Removal & Restoration, Shoreline Acquisitions
1 | Middle Duckabush wood-riparian restoration phase 1 | WFC, USFS, Tribes | 575000 | 575000 | 0 | PSP, USFS | Funding Strategy; Coordination |  | Feasibility/Design | 100000 | Feasibility/Design cont'd | 100000 | finish design concepts, scope LWD sources; riparian assessment | 19570 | 70% designs completed |  |  |  | Final Design | 75000 | Construction | 500000 |  |  | I,F,R | Mainstem | 0.5 miles | Place log jams and increase wood loading by helicopter and conventional means in strategic locations on Forest Service |  | 12,13 | 1.5 of 7 | 1,3 | 05-01-001 |  | Duckabush ELJ Design, Mid Duckabush ELJ Construction
1 | Lower and Middle Duckabush riparian-floodplain protection | Jefferson Co, JLT | 690000 | 690000 | 0 | PSP, RCO, Jefferson County, SRFB | Community Outreach |  | Begin Mid-HC Dosie Acquisition 2007 (Fire Station & Ruiz) | 303000 |  |  | Begin Mid-HC Dosie Acq'n 2009 (2 JLT parcels) | 375952 | Complete previous projects |  | funding |  | Community Outreach, Planning and Transactions | 690000 | Community Outreach, Planning and Transactions |  |  |  | L | Mainstem | 200 acres potential | Protect high quality habitats and purchase impaired habitats for future restoration; includes planning effort | HC SC Recovery Plan, Ch 9, p168-loss of riparian forest; Mid-Hood Canal Chinook Results Chain: "Protection: Acquisition and Regulatory Measures"; substrategies: "Conservation strategies implemented including purchase of properties & conservation easements" | 11,14 | 2,5.5 of 7 | 1,2,3,5 | 05-02-004 |  | Duckabush Riparian Habitat Acquisition
1 | Lower Duckabush riparian-floodplain restoration Phase 1 | WFC, Jefferson Co, JLT | 900000 | 680430 | 219570 | PSP, RCO, SRFB | [6 empty] | Reach Assessment, Landowner Outreach |  | Feasibility/Design, Landowner Outreach | ? | Finish designs and $ Strategy | 75000 | Finish designs and $ Strategy | 75000 | Funding, permit and Construction | 750000 |  |  | I,E,F,R | Mainstem | 0.5 miles | Improve instream wood loading rates and riparian conditions in the Lower Duckabush after protection efforts have advanced |  | 11 | 2 of 7 | 1,3 | 05-01-000 |  | Lower Duckabush riparian-floodplain restoration Phase 1
1 | USFS road decommission Duckabush | USFS, Tribes, HCSEG | 370500 | 370500 | 0 | USFS, federal aprop. | [12 empty] | Design, Permitting | 40000 | construction | 330500 |  |  | U | Headwater | 8.7 miles | Decommission high priority roads for aquatic risk or convert them to trails |  | 9,10 | 3 of 7 | 3,4,5 | 05-06-001 | 05-06-000 | USFS road decommission Duckabush
1 | SR101 Causeway Replacement Duckabush | Army Corps, WDFW, USFWS, TNC | 320000 | 300000 | 20000 | TNC, LNFF, ESRP, FHA, WSDOT, SRFB | 101 estuary causeway removal study completed previously | 132140 |  |  |  |  | 10% design PSNERP | 50000 | 35% design PSNERP | 50000 | Feasiblity and Design; community outreach | 20000 | More Design | 100000 | Final Design | 200000 |  |  | E | Estuary | ? | Continue PSNERP feasibility studies to address benefits for retrofit, alternatives, and costs along the Duckabush causeway |  | 2,3,5,6,7 | 4.5 of 7 | 1,2,3,7 | PA 01-01-002 | 05-03-002 | Duckabush SR101 Causeway Replacement and Estuary Restoration
1 | Pierce Creek culvert at Shorewood RD | Jefferson Co, JLT | 225000 | 225000 | 0 | PSP, ESRP, SRFB |  |  |  |  | Design | 10000 |  |  | property transactions | cost included above | Feasiblity and Design; community outreach |  | final design and permitting | 25000 | construction | 200000 |  |  | E,P | Estuary | 2 culverts; 1000ft | Improve tidal inundation and fish passage under Shorewood Road, improve upstream habitat and reduce flooding |  | 8 | 7 of 7 | 1,2,3,7 | 05-04-000 |  | Pierce Creek culvert at Shorewood RD
1 | Duckabush Fire Station Fill Removal | HCSEG, Jefferson Co | 175000 | 175000 | 0 | SRFB, PSAR |  |  |  |  | Design | 10000 |  |  | land transaction | costs included elsewhere | consider new approach to fire station |  | purchase, design, permit | 75000 | construction and planting | 100000 |  |  | E,R | Estuary | 2 acres | Remove landfill and replant streamside and upper estuary once property has been acquired |  |  | -- | 2,5 | 05-03-001 |  | Duckabush Fire Station Pierce slough Fill Removal
1 | Upper Hama Hama riparian restoration | USFS | 70000 | 70000 | 0 | USFS, federal aprop., other | [10 empty] | planting, exotic and upland control | 35000 | planting, exotic and kupland control | 35000 |  |  |  |  | R | Mainstem |  | Improve riparian conditions in non-anadromous reaches to address identified sediment and temperature inputs |  | 12,13,14 | 4.5 of 6.5 | 1,3,4,5 | 08-05-000 |  | Upper Hama Hama riparian restoration
1 | USFS road decommission Hamma Hamma | USFS, Tribes, HCSEG | 600000 | 600000 | 0 | USFS, federal aprop. | [10 empty] | Design, Permitting | 100000 | Permitting and Construction | 500000 |  |  |  |  | U | Headwater | 27.1 miles | Decommission high priority roads for aquatic risk or convert to trails |  | 7,8 | 6.5 of 6.5 | 3,4,5 | 08-06 |  | USFS road decommission Hamma Hamma
1 | USFS Road Drainage and Stabilization | USFS | 300000 | 300000 | 0 | USFS, federal approp. | [10 empty] | Permitting, Construction | 100000 | Permitting, Construction | 100000 | Permitting, Construction | 100000 |  |  | U | Headwater | ? | Stabilize high priority roads for aquatic risk; ongoing USFS maintenance across mid-HC rivers and beyond |  |  | Not modeled | 4,5 | 08-06 |  | USFS Road Drainage and Stabilization
|  |  | 6272201 |  |  |  |  | 296730 |  | 1072775 |  | 520000 |  | 1329922 |  | 881000 |  | 1910318 |  | 4361883
Skokomish-Lilliwaup
1 | Skokomish Estuary Restoration Phase 3- Skokomish Flats | MCD, Skokomish Tribe | 3452393 | 3452393 | 0 | ESRP, PSP, SRFB, NOAA | [6 empty] | Design, funding strategy | 25000 |  |  |  |  | permitting and construction | 3402393 | monitoring and adaptive management | 50000 |  |  | E | Estuary | 200+ acres, ~40 culverts | Lower berm in Phase 1 down further in limited area, remove bridge landing, topography modification, restore hydrology across Skok Flats RD and on TP access RD; 2014 to include barrier island access breaches etc | From Skokomish M&AM Results Chain: "Restore degraded estuarine and nearshore conditions"; substrategies: "Remove levees and landfill" and "Fill borrow ditches" |  |  | 2 | 10-03-002 | 10-03-004 | Skokomish Estuary Restoration Phase 3- Skokomish Flats, Phase 3C
1 | Skokomish Estuary Restoration Phase 4- Eastshore 6 acre fill removal | MCD, Skokomish Tribe | 450000 | 450000 | 0 | ESRP, PSP, SRFB, NOAA | [10 empty] | property transactions | 200000 | design, permitting, construction | 250000 |  |  |  |  | E, L | Estuary | 6 acres | Remove fill and old access road in the eastern cell of the lower Skokomish Estuary |  |  |  | 2,7 | 10-03-003 |  | Skokomish Estuary Restoration Phase 4- Eastshore 6 acre fill removal
1 | Lower Skabob Creek Complexity | MCD, Skokomish Tribe | 167060 | 120000 | 47060 | PSP-PSAR | [10 empty] | preliminary design | 47060 | design, permitting, construction | 120000 |  |  |  |  | E,I,W | Estuary | 4000 feet | Place woody debris by helicopter to improve rearing habitat in tidal creek system |  |  |  | 1,2,3,4,5 | 10-01-014 |  | Lower Skabob Creek Complexity
1 | Car Body Armor Removal | MCD, Skokomish Tribe | 143710 | 0 | 143710 | SRFB, PSP | [10 empty] | construction and planting | 143710 | [6 empty] | I, F | Mainstem | 1000 feet | Remove rock and/or car body riprap |  |  |  | 1,3,4,5 | 10-01-017 |  | Car Body Armor Removal
1 | Riparian plantings and noxious weed control | MCD, MNWCB, multiple | 800000 | 425305 | 374695 | NRCS, USDA, SRFB, PSP |  |  |  |  | design, scoping, planintg |  | scoping, planting, inventory and control | 404044 | scoping, planting, inventory and control |  | scoping, planting, inventory and control | 300000 | scoping, planting, inventory and control | 300000 | scoping, planting, inventory and control | 200000 |  |  | R, W | Mainstem and Tributaries | 200 acres | MCD and Mason County Noxious Weed Board to conduct outreach to private and public landowners to control knotweed and plant both agricultural openings and existing, alder-dominated riparian areas |  |  |  | 1,3,4,5 | 10-05-010 |  | Riparian plantings and noxious weed control
1 | North and South Fork Confluence Floodplain Restoration | MCD, Skokomish Tribe, multiple | 2449712 | 1900000 | 549712 | SRFB, PSP, Corps, Skokomish |  |  | coordinate with GI | 0 | coordinate with GI | 0 |  |  | design, permitting in mainstem, Vance | ? | landowner outreach and transactions | 400000 | design | 149712 | construction | 1900000 |  |  | I,F | Mainstem | 150 acres | This project will restore over 150 acres of mainstem floodplain between the historic and present confluences of the North and South Fork Skokomish by removing at least 3500ft of river dike, placing ~50 engineered log jams, and replanting |  |  |  | 1,3,4,5 | 10-01-015 | 10-01-020 | Skokomish Confluence Levee Design and Acquisition
1 | Vance Creek LWD and Armor Removal | MCD, Skokomish Tribe | 446757 | 446757 | 0 | [11 empty] | funding |  | design | 196757 | design and construct | 250000 |  |  | I, F | Mainstem | 2000ft | Implement designs developed with Bureau of Reclamation | From Skokomish M&AM Results Chain "Restore lower floodplain conditions"; substrategy " Remove impediments to meander, avulsion, and channel connectivity" |  |  | 1,3,4,5 | 10-01-031 |  | Vance Creek LWD and Armor Removal
1 | Farm Plans, and BMPs | MCD, multiple | 300000 | 200000 | 100000 | NRCS, MCD, Landowner | landowner outreach, fencing, farm plans, | 50000 | landowner outreach, fencing, farm plans, | 50000 | landowner outreach, fencing, farm plans, | 50000 | landowner outreach, fencing, farm plans, | 100000 | landowner outreach, fencing, farm plans, | 100000 | landowner outreach, fencing, farm plans, | 100000 | landowner outreach, fencing, farm plans, | 100000 | landowner outreach, fencing, farm plans, | 100000 |  |  | R, W | Mainstem and Tributaries | 2 miles | Work with Mason Conservation District and private landowners to improve stewardship through public incentive programs such as Farm Plans Cost Share, Environment Quality Improvement Program, Wildlife Habitat Improvement Program, and BMP construction |  |  |  | 1,3,4,5 | Not in HWS |  | Farm Plans, and BMPs
1 | ELJs in North Fork | Skokomish Tribe, Fish Committee | 1300000 | 1200000 | 100000 | TP, Skokomish |  |  |  |  | Global agreement |  | FERC license issued?, recovery plan finalized, project planning |  | reach assessment, concept design | ? | Reach assessment and planning | 100000 | Design and permitting | 200000 | construction | 1000000 |  |  | I,F | Tributary | multiple miles | License agreement requires Fish and Habitat Committee develop Restoration plan after a couple of years of assessment |  |  |  | 1,3,4,5 | 10-01-021 |  | ELJs in North Fork
4 | Frigid Creek Culvert Replacement | GD, USFS, MCD | 227236 | 227236 | 0 | GD, Joint Venture |  |  |  |  | scoping |  | preliminary design |  | design and permitting | 27236 | design | 27236 | construction | 200000 |  |  |  |  | P | Tributary | remove 2 barriers | 2 fish passage projects at upper extent of Frigid Creek for steelhead (?), coho (?) and cutthroat |  |  |  | 1,3,5,6,7 | 10-04-001 |  | Frigid Creek Culvert Replacement
1 | Holman Flats Floodplain Restoration Phase 2 | Skokomish Tribe, USFS | 932252 | 932252 | 0 | SRFB,PSP, USFWS,NFWF, USFS, TP |  |  | feasibility | 63500 | design, permitting | 140000 | final design, wood stockpiling, construction | 1030000 | monitoring, begin funding strategy for Phase 2 on TP land | ? | funding strategy |  | design and planning | 120000 | construction | 812252 |  |  | I,F | Tributary | 1 mile | Phase 2 in Tacoma Power section of Holman Flats; construct engineered log jams |  |  |  | 1,3,4,5 | 10-01-007 |  | Holman Flats Floodplain Restoration Phase 2
1 | South Fork Skok LWD Enhancement Phase 3 | MCD, Skokomish | 1775774 | 1775774 | 0 | SRFB, PSAR, in kind | [10 empty] | Funding |  | Restoration | 1775774 |  |  |  |  | I,F | Tributary | .85 mile, 16 ELJs | This phase of the project extends over 1 mile downstream of Phase I and II, and involves installing 16 engineered log jams. | From Skokomish M&AM Results Chain "Restore upper watershed conditions in South Fork and major tributaries"; substrategy "Increase woody debris and log jam density" |  |  |  | 10-01-016 |  | South Fork Skok LWD Enhancement Phase 3
1 | Upper South Fork and Tributary Floodplain-Channel-Riparian Restoration Assessment and Design | Skokomish Tribe, USFS | 300000 | 300000 | 0 | SRFB, PSP, stewardship receipts | [10 empty] | LWD assessment and conceptual | 150000 | Design and permitting | 150000 |  |  |  |  | I,F | Tributary | 10 miles | Recovery plan diagnoses the upper South Fork watershed as producing sediments and channel instability beyond reference levels from both faulty roads/logging as well as instream channel incision/terrace erosion. This assessment would determine the extent of degradation and lay out a road map for restoration for coming years. |  |  |  | 1,3,4,5 | Not in HWS yet |  | Upper South Fork and Tributary Floodplain-Channel-Riparian Restoration Assessment and Design
1 | USFS Road Decommission - North Fork 14km | USFS and SWAT | 330000 | 330000 | 0 | federal approp., SRFB, PSP, EPA, USFS | [10 empty] | design, permitting | 30000 | construction | 300000 |  |  |  |  | U | Headwaters | 8.7 miles | Decommission high priority roads for aquatic risk |  |  |  | 4,5,6,7 | 10-06-004 |  | USFS Road Decommission - North Fork 14km
1 | USFS Road Decommission - South Fork 18.4 miles | USFS, SWAT | 2455000 | 2000000 | 455000 | federal approp., SRFB, PSP, EPA, USFS | construction, design, permitting | ? | construction, design, permitting | 600000 | construction, design, permitting | 3010020 | construction, design, permitting | 3511690 | construction, design, permitting | 2911690 | construction, design, permitting | 1455000 | construction | 1000000 |  |  |  |  | U | Headwaters | 18.4 miles | Decommission last remaining priority roads on the Forest in this basin |  |  |  | 4,5,6,7 | 10-06-003 |  | USFS Road Decommission - South Fork 18.4 miles
1 | USFS Road Decommission - Vance Creek 6km | USFS, SWAT | 230000 | 230000 | 0 | federal approp., SRFB, PSP, EPA, USFS | [10 empty] | design, permitting | 30000 | construction | 200000 |  |  |  |  | U | Headwaters | 3.7 miles | Decommission high priority roads for aquatic risk |  |  |  | 4,5,6,7 | 10-06-011 |  | USFS Road Decommission - Vance Creek 6km
1 | Silviculture Treatments for increased hydrologic maturity | USFS, SWAT | 0 | ? | ? | timber sale |  |  |  |  | design, permitting | ? | implementation, design, permitting | ? | implementation, design, permitting | ? | implementation for South Fork | [7 empty] | U | Headwaters | 800 acres | Increase hydrologic maturity within Skokomish basin |  |  |  | 1,5,6 | Not in HWS |  | Silviculture Treatments for increased hydrologic maturity
1 | Road Drainage and Stabilization - South Fork | USFS, SWAT | 0 | ? | ? | federal approp., SRFB, PSP, EPA, USFS | planning, permitting, construction | ? | planning, permitting, construction | 638460 | construction, BMPs | 744970 | construction, BMPs | 744970 | ? | ? | construction |  | construction |  | construction |  |  |  | U | Headwaters | 149 miles | Stabilize roads to reduce aquatic risk |  |  |  | 4,5,6,7 | 10-06-002 |  | Road Drainage and Stabilization - South Fork
1 | Road Maintenance | USFS, SWAT | 0 | ? | ? | federal approp., SRFB, PSP, EPA, USFS | construction | ? | construction | 142875 | construction | 166688 | construction | 166687 | construction | ? | maintenance |  | maintenance |  | maintenance |  |  |  | U | Headwaters | ? | Maintain roads to reduce aquatic risk through annual maintenance program |  |  |  | 4,5,6,7 | Not in HWS |  | Road Maintenance
1 | Lilliwaup Instream Restoration | LLTK | 805832 | 0 | 805832 | SRFB, in-kind, PSAR | [6 empty] | assessment and design | 60000 | final design and funding strategy | 55500 | construction and planting | 805832 | monitoring | [5 empty] | I,E,R,F | Mainstem | 0.5miles | Work with landowners to implement restoration projects to remove fill and aggraded sediments in lower floodplain, enhance woody debris, and replant riparian areas |  |  |  | 1,2,3,7 | 09-01-002 |  | Lilliwaup Instream Restoration
1 | Skokomish River GI 2014 | MCD, Mason Co | 2451757 | 360500 | 2091257 | SRFB, PSAR |  | 50000 |  | 1494835 |  | 4111678 |  | 6017391 |  | 3094426 | Planning | 2451757 | Planning | [6 empty] | Mainstem |  | effort is now in its final phase, which is to complete feasibility-level (35%) designs and an environmental impact statement with public review and present them to Congress for funding. | Skokomish Recovery Plan, Ch4, p121-122 |  |  |  | 10-01-029 |  | Skokomish River GI 2014
1 | Mainstem Skokomish LWD Design | MCD, Skokomish | 247858 | 247858 | 0 | SRFB, PSAR, in kind | [12 empty] | Planning | 247858 |  |  |  |  | I | Mainstem | 26.8 acres, 1.60 miles | This project will involve developing a plan to improve habitat complexity in this reach | From Skokomish M&AM Results Chain "Restore lower floodplain conditions"; substrategy "Construct ELJs and install log jams to restore channel complexity and sediment processes" |  |  |  | 10-01-030 |  | Mainstem Skokomish LWD Design
| S. Fork Skokomish Canyon Fish Passage Assessment | MCD, Skokomish | 164630 | 164630 | 0 | SRFB/PSAR | [12 empty] | Planning | 164630 |  |  |  |  | P | Tributary | 23 miles, 111 acres | Assess the four sites identified by WDF to determine the passability at various flows and develop design concepts for fish passage improvements if necessary. Fish passage in this location will be necessary for successful re-introduction of Chinook into the upper South Fork. | From Skokomish M&AM Results Chain "Restore upper watershed conditions in South Fork and major tributaries"; substrategy "Improve adult passage at the gorge cascades" |  |  |  | 10-04-003 |  | S. Fork Skokomish Canyon Fish Passage Assessment
1 | Skokomish River Natural Process Rehabilitation | MCD, Skokomish | 10823972 | 8332972 | 2491000 | SRFB/PSAR Large Capital | [12 empty] | Planning & Restoration | 10823972 | Planning & Restoration |  |  |  | I,F E | Mainstem | 208 acres | This project focuses on restoring channel structure, floodplain connection, availability of off-channel habitat, and estuarine function. The Army Corps of Engineers (ACOE) has been working in partnership with many watershed stakeholders on a watershed scale strategy for restoration since 1997 | From Skokomish M&AM Results Chains "Restore lower floodplain conditions"; "Restore upper watershed conditions in SF and major tributaries"; and "Restore estuarine and nearshore conditions" |  |  |  | 10-01-032 |  | Skokomish River Natural Process Rehabilitation
|  |  | 30253943 |  |  |  |  | 50000 |  | 2939670 |  | 8173356 |  | 11530738 |  | 6088852 |  | 6240595 |  | 19701096 |  | 4312252
Eastern Straits
1 | Discovery Bay (snow/salmon) Railroad Grade Removal | NOSC, WDFW, JCD | 1508592 | 1508592 | 0 | NOAA, PSP | [12 empty] | construction | 1508592 |  |  |  |  | E | Estuary | 15 ac 3400' RR grade removal | Implement selected alternative to remove abandoned railroad grade in southern estuary between Snow and Salmon Creeks |  |  |  | 2,3,5,7 | 01-03-006 |  | Discovery Bay (snow/salmon) Railroad Grade Removal
1 | Snow Creek Delta Cone and Estuary Restoration | NOSC, WDFW, JCD | 700000 | 700000 | 0 | NOAA, PSP, NRCS | [8 empty] | further scoping and funding strategy | 0 |  |  |  |  | construction | 700000 |  |  | E | Estuary | 12 acres | Implement selected alternative to restore floodplain and tidal prism below SR101, as scoped by the RR Grade Removal study and Delta Cone Removal and Estuary Design |  |  |  | 2,3,5 | 01-03-009 |  | Snow Creek Delta Cone and Estuary Restoration
1 | Maynard Nearshore Restoration | NOSC, WDFW, JCD, JMRC | 568932 | 568932 | 0 | JCMRC,SRFB | [6 empty] | further scoping and funding strategy | 0 | final design and construction | 200000 | final design and permiting |  | construction | 568932 |  |  |  |  | E | Estuary | 10 acres | Implement selected alternative to enhance railroad grade in northwestern estuary, including riprap removal, cherry pond connection, contaminated sediments, forage fish, small stream culvert daylighting, and bridge removal |  |  |  | 2,3,5 | 01-03-004 |  | Maynard Nearshore Restoration
1 | Snow/Salmon Reconnection Feasibility and Design | WDFW, NOSC, JCD, TNC, PSNERP | 20000 | 20000 | 0 | PSNERP, LNFF | feasibility, planning | 10000 | Put on hold due to hydrology impacts on adjacent structures/bridge and landowner issues | 0 | further scoping |  | further scoping |  | further scoping |  | further scoping | 10000 |  |  | further scoping | 10000 |  |  | I,W,R,F | Mainstem | 1 mile | Assess benefits and feasiblity of reconnecting Snow and Salmon Creeks; design construction plans |  |  |  | 1,2,3,6 | 01-01-001 |  | Snow/Salmon Reconnection Feasibility and Design
1 | SR101 Bridge/Causeway Replacement Feasibility | PSNERP, DOT | 20000 | 10000 | 10000 | PSNERP, LNFF | [12 empty] | further scoping | 10000 | further scoping | 10000 |  |  | I,W,E,F | Estuary | 1miles | Assess benefits and feasiblity of widening the bridge and shortening causeway of State Route 101 crossing in Lower Discovery Bay to allow reconnection of Snow and Salmon and improve tidal hydrology |  |  |  | 1,2,7 | 01-03-010 |  | SR101 Bridge/Causeway Replacement Feasibility
1 | West Uncas Road Culvert Design | NOSC, Jefferson Co, WDFW | 98200 | 98200 | 0 | NOAA, American Rivers, PSP-PIDA, JC |  |  |  |  | Design and survey | 10000 | redesign and temporary passage construction | 1000 |  |  | complete designs; preliminary engineering | 98200 | [6 empty] | I,P,F | Mainstem | 0.25 miles | Assess design options and costs for replacing culvert with bridge to ease passage and restore habitat forming processes, including road vacation; temporarily provide for passage with sand bag weirs. |  |  |  | 1,3,4,7 | 01-04-002 |  | West Uncas Road Culvert Design
1 | West Uncas Road Culvert Replacement | NOSC, JCD, WDFW, Jefferson Co | 400000 | 400000 | 0 | PSAR, Jefferson County | [10 empty] | funding strategy |  |  |  | construction | 400000 |  |  | I,P,F | Mainstem | 1 mile | Implement selected alternative from above to address West Unca's RD culvert passage problem |  |  |  | 1,3,4,7 | 01-04-001 |  | West Uncas Road Culvert Replacement
1 | Mid-Salmon Creek Floodplain Restoration | JSKT, NOSC, Jefferson Co, JCD | 500000 | 500000 | 0 | PSAR, SRFB, NOAA, USFWS | [10 empty] | continue scoping discussions and outreach |  |  |  | land transactions and preliminary design | 500000 | final designs and funding strategy | 175000 | AR, I, R, F | Mainstem | 0.5 miles | Investigate feasibility of restoring the middle reach of salmon creek (adjacent to Unca's RD) back to original location, while improving fish passage barrier, instream and riparian conditions |  |  |  | 1,3,4,5 |  |  | Mid-Salmon Creek Floodplain Restoration
1 | Snow Creek LWD Restoration Design | NOSC, JCD | 100000 | 100000 | 0 | PSP, SRFB | [12 empty] | landowner contacts and survey | 50000 | preliminary design | 50000 |  |  | I | Mainstem | 1 mile | Landowner outreach, feasibility, and design of project to improve channel complexity and instream functions through summer chum range |  |  |  | 1,3,4 | 01-01-002 |  | Snow Creek LWD Restoration Design
1 | Snow/Salmon Creek Sediment Investigation | NOSC, JCD, USFS | 100000 | 100000 | 0 | PSP, SRFB | [12 empty] | landowner contacts and survey | 50000 | preliminary design | 50000 |  |  | U | Headwaters | ? | Limiting habitat factors assessments have identified sediment as a major factor for salmonid decline. This project would work with major headwater owners of public and private forestlands and road networks to ID most likely sources and address them |  |  |  | 4,5,6 |  |  | Snow/Salmon Creek Sediment Investigation
1 | Snow/Salmon Road Decommissioning and Stabilization | USFS, NOSC | 30000 | 30000 | 0 | USFS, SRFB,PSP | [14 empty] | Design | 30000 | Permitting and construction | 120000 | U | Headwaters | 7 miles | Decommission, convert to trail, or stabilize highest priority roads for aquatic risk |  |  |  | 4,5,6,7 | 01-06-001; 01-06-002; 01-06-003; 01-06-004; 01-06-005 |  | Snow/Salmon Road Decommissioning and Stabilization
2 | Kilisut Harbor/Oak Bay Reconnection | JSKT, WSDOT, WDFW, NOSC | 12738089 | 9438089 | 3300000 | WSDOT, ESRP, USACE, PSAR |  |  | discussion | 0 | discussion | 0 | Discussion | 0 | feasiblity from PSNERP, 30% design, funding strategy | 20000 | design | 200000 | permitting and construction |  | construction | 12538089 |  |  | M,P | Marine | 100 acres | Replace undersized culverts with bridge length on Marrowstone Island causeway to restore natural tidal inundation and access to and from Scow Bay for Puget Sound and Hood Canal salmon stocks | Puget Sound Chinook Nearshore Chapter, p 150-151; HC Summer Chum Recovery Plan, Ch11, p214, 8- Oak Bay segment ranked highest (tied with Skokomish west shore) among estuarine-marine aresa for potential benefits of restoration; HC SC Recovery Plan, Appendix B, Ch 3, fig 7- Kilisut Harbor located in Oak Bay segment |  |  | 2,7 | 07-02-002 | 07-02-003 | Kilisut Harbor/Oak Bay Reconnection
4 | Fort Townsend State Park Shoreline Restoration | MRC, State Parks | 250000 | 250000 | 0 | NWSI, State Parks |  |  |  |  | discussion | 0 | funding strategy | 0 |  |  | funding strategy and design | 25000 | final design | 25000 | construction | 200000 |  |  | M | Marine | 300 feet, 1 acre | State Parks would like to restore the marine shoreline by pulling back fill and riprap while preserving pedestrian access to the beach |  |  |  | 2 | 07-02-001 |  | Fort Townsend State Park Shoreline Restoration
| Snow Creek Watershed Acquisition and Restoration | JLT | 342850 | 0 | 342850 | SRFB, PSAR |  | 10000 |  | 0 |  | 10000 |  | 1000 |  | 220000 | Acquisition | 342850 | restoration | [8 empty] | fee-simple purchase and restoration of a 21.5-acre parcel that is bisected by ~1550' of Andrews Creek at its exit from Crocker Lake. |  |  |  |  | 01-02-013 |  | Snow Creek Watershed Acquisition and Restoration
| East Jefferson Summer Chum Riparian Phase II | NOSC | 230000 | 0 | 230000 | SRFB, PSAR | [10 empty] | planting | 230000 | [9 empty] | increase the acreage of riparian plantings to restore critical ESA-listed Hood Canal Summer Chum habitat. |  |  |  |  | 01-05-017 |  | EastJefferson Summer Chum Riparian Phase II
|  |  | 17606663 |  |  |  |  | 20000 |  | 0 |  | 20000 |  | 2000 |  | 440000 |  | 906050 |  | 2212524 |  | 14488089
Quilcene
2 or 4 | Tarboo/Dabob Bay Protection | NWI, TNC, DNR, Tribes, JLT | 2500000 | 1150000 | 1350000 | USFWS, SRFB, ESRP, Trust Land Transfer |  |  | Transactions | 2000000 | transactions | 5000000 | Transactions | 10000000 | Transactions | 10000000 | transactions | 1500000 | transactions | 500000 | transactions | 500000 |  |  | M,L | Marine | 118 acres | Protection of state timber and private lands within the 3,600 acre Dabob Bay Natural Area to protect ecosystem functions and processes, and diverse habitats in one of the highest quality and largest saltmarsh estuaries remaining in the Hood Canal and Straits of Juan de Fuca region. The project includes acquisition of 1,400 acres of private lands from willing landowners and use of Trust Land Transfer funds for State lands. |  |  |  | 2 | 06-02 |  | Tarboo/Dabob Bay Protection
2 or 4 | Tarboo/Dabob Bay Nearshore Restoration | NWI, TNC, DNR, Tribes, JLT | 350000 | 300000 | 50000 | USFWS, NOAA, ESRP, SRFB, NFWF |  |  | landowner outreach, early projects | 40000 | landowner outreach, design and permitting | 60000 | landowner outreach, construction, more design | 200000 | landowner outreach, construction, more design | 1000000 | design and funding; invasive control | 60000 | construction; invasive control | 140000 | invasive control | 150000 |  |  | M | Marine | 300ft; 3000acres | Remove rock and creosote bulkheads, plant, and control invasive species in shoreline riparian forests at priority restoration sites within Tarboo-Dabob Bay. |  |  |  | 2,5 | Not in HWS |  | Dabob Bay Creosote Bulkhead Removal
4 | Tarboo Fish Passage | NWI | 310001 | 310001 | 0 | NOAA, USFWS, NFWF | [10 empty] | funding strategy | 155000 | design and construction | 155001 |  |  |  |  | P | Mainstem | ? | Replace undersized culverts on East Fork Tarboo Creek and retrofit mainstem culverts funded in previous SRFB rounds to ensure function and fish passage. |  |  |  | 7 | 06-04 |  | Tarboo Fish Passage
1 | Lower Biq Quilcene River & Estuary Master Plan | Jefferson Co, TNC, HCSEG, WDFW | 254000 | 0 | 254000 | PSP, SRFB, NFWF, PSAR-PIDA | finish linger longer assessment | 60000 | Develop funding strategy; continue land transactions as appropriate | 0 |  |  | funding strategy and 10% design | see south bank levee above | 35% Design | see south bank levee above | community outreach and conceptual design | 54000 | preliminary and final designs; | 200000 |  |  |  |  | I,W,E,L,R,F | Mainstem and Estuary | 4000ft; 250 acres | Continue Linger Longer Reach Restoration with the end goal of restoring floodplain processes below Rogers Street and reconnecting freshwater and tidal link. TNC to lead outreach and HCSEG to lead design; work with shellfish industry. This project will include widening the floodplain, creating increased channel habitat, widening the existing bridge, and removing last estuary dike on north bank and delta cone. PSNERP funded 10% design and Navy funded limited additional investigation. |  |  |  | 1,2,3,6,7 | 03-01-001 | 03-03-009, 011, 013, 014 | Lower Biq Quilcene River & Estuary Master Plan
1 | Big Quilcene Estuary South Bank Levee and Delta Cone Removal | HCSEG, TNC, WDFW | 1100000 | 1100000 | 0 | PSAR, SRFB, ESRP, NFWF | [6 empty] | funding strategy and 10% design | 20000 | 35% Design | 100000 |  |  | construction | 1100000 |  |  |  |  | E | Estuary | 2000 feet, 50+acres | Implement Master Plan by removing south bank levee and delta cone upland materials, as designed and supported by community and shellfish industry |  |  |  | 1,2,3,6,7 | 03-03-011 | add delta cone link | Big Quilcene Estuary South Bank Levee and Delta Cone Removal
1 | Big Quilcene Linger Longer Reach Restoration | Jefferson Co, TNC, HCSEG, WDFW | 4400000 | 4400000 | 0 | PSAR, SRFB, ESRP, NFWF | [10 empty] | land transactions | 400000 | construction | 4000000 |  |  |  |  | M, E | Mainstem | 4000ft; 250 acres | Implement Master Plan by replacing Linger Longer road and bridge with new thoroughfare on elevated bridge. Reconstruct river channel as designed and supported by community and shellfish industry |  |  |  | 1,2,3,6,7 |  |  | Big Quilcene Linger Longer Reach Restoration
1 | Big Quilcene River Habitat Restoration Phase 3 | Skokomish Tribe, HCSEG | 400000 | 400000 | 0 | SRFB, Skokomish Tribe, PSAR | design, permitting | 70000 | design, levee removal study (see below) | 60000 | construct phase 1, design phase 2 | 320000 | construct phase 2 | 775000 | Design Phase 3 | ? | design and permit and fund | 50000 | construct phase 3, monitoring; further design? | 350000 |  |  |  |  | I,F | Mainstem | 4000 feet | Place woody debris to improve channel and floodplain complexity and instream functions through summer chum range |  |  |  | 1,3 | 03-01-004, 03-01-005, 03-01-006, 03-01-007, 03-01-009, 03-01-010 | 03-01-008, | Big Quilcene River Habitat Restoration Phase 3
1 | Little Quilcene Mclanahan Reach Feasibility and Design | HCSEG | 50000 | 50000 | 0 | PSAR, SRFB, NFWF, USFWS | [10 empty] | design and community outreach | 50000 | [6 empty] | I,F | Mainstem | 2000 feet | Complete feasibility and design for instream and floodplain restoration in lower river below Center Road |  |  | add | 1,3 | 03-01-015 |  | Little Quilcene Mclanahan Reach Feasibility and Design
1 | Little Quilcene Mclanahan Reach Restoration | HCSEG | 250000 | 250000 | 0 | PSAR, SRFB, NFWF, USFWS | land transaction (not included in cost) | [7 empty] | analysis and feasibility | 50000 |  |  | permitting and construction | 250000 |  |  |  |  | I,F | Mainstem | 2000 feet | Remove riprap and add wood to restore floodplain and channel habitats in lower river below Center Road |  |  |  | 1,3 | 03-01-016 |  | Little Quilcene Mclanahan Reach Restoration
1 | Lower Big Quilcene River Riparian Protection | JLT | 189600 |  | 0 | [13 empty] | Acquisition and Restoration | 189600 | [7 empty] | protect a14-acre parcel that includes approximately 1/4 mile of riparian habitat along both sides of the river, and upland forest extending up 200 vertical feet on the south side of the river | HC SC Recovery Plan, Ch 8, p136-Protection of Freshwater Reaches; p138-Loss of Riparian Forest |  |  |  | 03-02-016 |  | Lower Big Quilcene River Riparian Protection
|  |  | 9803601 | [14 empty] | 2269000 |  | 6884601 |  | 650000
Union and Tahuya |  |  | 0
1, 4 | Union Estuary Johnson Farm Restoration -Construction | HCSEG, WDFW, PNWSC | 125000 | 125000 | 0 | federal, SRFB, NRCS | [10 empty] | Lower Mendy Creek improvements | 125000 | [6 empty] | E,R,L | Estuary | 41 acres | Construct - Breach levees strategically and enhance tidal channels and flats to restore tidal inundation to 40 acres of historic salt marsh; bridge breaches with boardwalks; revegetate backshore; enhance adjacent channels. Mid to upper Mendy Creek is Domain 4. |  |  |  | 1,2,3,7 | 11-03-003 |  | Union Estuary Johnson Farm Restoration -Construction
1 | Beards Cove Union River Estuary | WDFW, GPC | 1082000 | 1082000 | 0 | SRFB/PSAR | [10 empty] | Permitting and funding |  | permitting and construction | 1082000 | [6 empty] | 19 acres | Design and restore the union river estuary on the 'Beards Cove' parcels | HC Summer Chum Recovery Plan, Ch11, p230-Remove fill, pool, infrastructure east of Klingle Wetlands and restore lost salt marsh habitat |  |  | 2, 7 | 11-03-005 |  | Beards Cove Union River Estuary
1 | Lower Union River Habitat Assessment and Feasibility | HCSEG | 97908 | 97908 | 0 | SRFB, NFWF, WDFW, USFWS,PSP | implement several smaller projects | ? | survey and design 2 LIP projects | ? | construct 2 LIP projects Union; lower tahuya reach assessment and design for LWD | 309337 |  |  | construct Tahuya LWD | 203015 | funding strategy |  | planning | 97908 |  |  |  |  | I, W, R, F | Mainstem | 5000ft | Assess opportunities for improving instream and floodplain conditions | HC Summer Chum Recovery Plan, Ch 11, p217- Estuarine habitat loss and degradation |  |  | 1,3,4, 5 | 11-01-001 |  | Lower Union River Habitat Assessment and Feasibility
1 | Lower Union River Instream Enhancement | HCSEG | 350000 | 350000 | 0 | SRFB, NFWF, WDFW, USFWS,PSP | implement several smaller projects | ? | survey and design 2 LIP projects | ? | construct 2 LIP projects Union; lower tahuya reach assessment and design for LWD | 309337 |  |  | construct Tahuya LWD | 203015 | funding strategy |  | final design, permitting and construction of Phase 1 | 350000 |  |  |  |  | I, W, R, F | Mainstem | 5000ft | Add wood in summer chum range to restore instream and floodplain conditions |  |  |  | 1,3,4, 5 |  |  | Lower Union River Instream Enhancement
2 | Tahuya River LWD Placement, Phase 3 | HCSEG | 280000 | 280000 | 0 | SRFB, PSAR, NFWF, USFWS | [10 empty] | funding strategy and design | 30000 | permitting and construction | 250000 |  |  |  |  | I, W, R, F | Mainstem | 5000ft | Add wood in summer chum range to restore instream and floodplain conditions |  |  |  | 1,3,4,5 | 12-01-004 |  | Tahuya River LWD Placement, Phase 3
2 | Tahuya River Northshore Road Bridge Replacement | Mason Co | 240000 | 240000 | 0 | PSNERP | [10 empty] | Feasiblity and Design; community outreach | 20000 | More Design | 20000 | Final Design | 200000 |  |  | E | Estuary | ? | Continue PSNERP feasibility studies to address benefits for retrofit, alternatives, and costs along the Tahuya causeway |  |  |  | 1,2,7 |  |  | Tahuya River Northshore Road Bridge Replacement
2 | Tahuya Priority Lands Conservation | GPC, WDFW, DNR, HC Alliance | 4474059 | 4474059 | 0 | PSAR |  |  |  |  | Design and partner building; funding | ? |  |  | Design and partner building; funding | ? | funding strategy | 0 | Appraisal, Negotiations | 70000 | Transactions | 4404059 |  |  | L | Headwaters | 3500 acres | Continue conservation efforts with the Hood Canal Alliance |  |  |  | 1,3,4,5,6 | Not in HWS |  | Big Beef to Dewatto Priority Lands Conservation
| Tahuya Watershed Stream Barrier Inventory | DNR/MCD | 287114 | [13 empty] | planning | 287114 | [9 empty] | Fish passage barrier inventory of the Mason County portion of the Tahuya Peninsula. | WRIA 15 Limiting Factors Analysis, p150- access & passage; p226-data gaps |  |  |  | 12-04-016 |  | Tahuya Watershed Stream Barrier Inventory
|  |  | 6936081 | [14 empty] | 462114 |  | 1869908 |  | 4604059
West Kitsap |  |  | 0
2 | IMW Lower Big Beef Restoration | HCSEG | 1247667 | 1247667 | 0 | SRFB, PSAR, |  |  | Project Development |  | Preliminary Design and funding strategy | ? | Final Design, permitting | 79000 |  |  | funding strategy |  | restoration | 1247667 |  |  |  |  | I | Mainstem | 11 acres; 1 mile | WDFW, HCSEG, UW effort to restore well road removal, instream wood structures, wetlands and side channel habitat in lower watershed on UW property; treatment associated with IMW program | HC Summer Chum Recovery Plan, Ch12, p253-255-UW Research Station; Big Beef Cr Preservation; Remove UW Service Road & Fill; Intensively Monitored Watershed Plan: p17-B Beef Cr. Control sediment delivery/routing, temperature, low summer discharge |  |  | 1,3,4,5,6,7 | 15-01-006 |  | Lower Big Beef Creek Restoration- Construction
2 | IMW Fish Weir Modification | WDFW | 390000 | 390000 | 0 | NOAA | [10 empty] | funding strategy |  | design | 40000 | construction | 350000 |  |  | I, E | Mainstem | 5 acres | Upgrade fish weir to require less instream sediment management and improve habitat conditions |  |  |  | 1,2,3,4,5,6,7 |  |  | IMW Fish Weir Modification
2 | IMW Middle Big Beef Restoration, Phase 2 | HCSEG | 500000 | 500000 | 0 | SRFB, PSAR, USFWS, NOAA |  |  | Project Development |  | Preliminary Design and funding strategy | ? | Final Design, permitting | 79000 |  |  |  |  | funding strategy |  | design and construction | 500000 |  |  | I | Mainstem | 200 acres; 2 miles | Restore woody debris loading in middle reaches above UW property and below Lake Symington through helicopter installations; treatment associated with IMW program |  |  |  | 1,3,4,5,6,7 | 15-01-000 | 15-01-005 | IMW Middle Big Beef Restoration, Phase 2
2 | Dewatto Estuary | HCSEG | 400000 | 400000 | 0 | PSP, SRFB, ESRP, coastal wetlands | [10 empty] | funding strategy |  | design | 20000 | permitting, construction | 380000 |  |  | E | Estuary | 20 acres | Remove relict levees in sub-estuary and restore channel complexity; fill dredge hole; replant affected riparian areas |  |  |  | 2,7 | 13-03-000 |  | Dewatto Estuary
| IMW Little Anderson LWD Phase 3 | HCSEG | 246647 | 246647 | 0 | SRFB, USFWS, NOAA | [10 empty] | funding strategy |  | design | 50000 | construction | 300000 |  |  | I | Mainstem | 0.5 miles | Next Phase of installing LWD in Little Anderson Cr. | Intensively Monitored Watershed Plan: p17-LAnderson Cr. Habitat complexity, sediment routing, water delivery/routing, off-channel habitat, LWD |  |  | 1,3,4,5 | 16-01-003 |  | IMW Little Anderson LWD Phase 3
4 | Martha John Creek Estuary Conservation Plan | GPC, PG S'Klallam Tribe | 47500 | 0 | 47500 | NFWF |  |  |  |  | conservation plan development | 47500 | continue plan development |  |  |  | planning | 47500 | [6 empty] | L, I, W, E, R | Mainstem | 1 Mile | Engage key landowners in development of a conservation plan for Martha John Creek estuary and lower reach, resulting in a strategic conservation plan implemented by mulitple organizations |  |  |  | 1,2,3 | 16-02-002 |  | Martha John Creek Estuary Conservaiton Plan
|  |  | 2935167 |  |  |  |  | 0 |  | 0 |  | 47500 |  | 158000 |  | 0 |  | 47500 |  | 1357667 |  | 1530000
Dungeness and Jimmycomelately (only summer chum stocks considered in HCCC process) |  |  | 0
3 | Dungeness River Large Wood Restoration |  | 0 |  |  | SRFB, PSAR, Donations, BIA | [10 empty] | Feasibility Pending | [7 empty] | I,R |  | 50 ELJs | Build approximately 50 engineered and design/build logjams (ELJ's and DBLJ's) in the Dungeness River from river mile (RM) 2.7 to 18.8 and in the Gray Wolf River from RM 0.0 to 2.0. |  |  |  | 1 |  |  | Dungeness River Large Wood Restoration
3 | Dungeness River Riparian Habitat Protection | JSKT | 0 |  |  | SRFB, EPA, PSAR | [10 empty] | Feasibility Pending | [7 empty] | R,E |  | 4 miles | The project will protect many previously identified Dungeness River riparian properties downstream of DNR ownership (approximately river mile 12.0) through the purchase of property and conservation easements. |  |  |  | 1,3,5 |  |  | Dungeness River Riparian Habitat Protection
3 | Dungeness River Riparian Restoration |  | 0 |  |  | SRFB | [10 empty] | Feasibility Completed | [7 empty] | R |  | 14 miles | Riparian restoration involves three interrelated actions: to eliminate or control noxious weeds, plant unproductive or non-forested sites with appropriate shrubs and trees, and maintain the site until the desired forest community is established (5 years or more). |  |  |  | 1,3 |  |  | Dungeness River Riparian Restoration
3 | Dungeness River Instream Flow Restoration – Irrigation Efficiencies |  | 0 |  |  | SRFB, PSAR, WCC | [10 empty] | Design Completed | [7 empty] | I,R |  | 5 cf/s | This suite of projects includes multiple interrelated strategies that restore stream flows in the Dungeness River. One strategy is irrigation water conservation - primarily, irrigation ditch piping. |  |  |  | 6 |  |  | Dungeness River Instream Flow Restoration – Irrigation Efficiencies
3 | Dungeness River Instream Flow Restoration - Storage |  | 0 |  |  | SRFB | [10 empty] | Feasibility Completed | [7 empty] | I,R |  | 5 cf/s | This suite of projects includes interrelated water storage strategies that contribute to Dungeness River late season stream flow restoration. These strategies include water storage in small off-channel reservoirs and shallow aquifer recharge (SAR). |  |  |  | 6 |  |  | Dungeness River Instream Flow Restoration - Storage
3 | Dungeness River Floodplain Restoration | Clallam Co | 0 |  |  | SRFB, PSAR, Corps | [10 empty] | Feasibility Completed | [7 empty] | I,R |  | 5000 ft | This project is floodplain restoration through the setback or reconfiguration of dikes or armored banks, from the mouth to Canyon Creek (RM 0 to 10.7). |  |  |  | 1,3,4,5,6,7 |  |  | Dungeness River Floodplain Restoration
2+ | Dungeness Drift Cell Conservation |  | 0 | [13 empty] | Feasibility Completed | [7 empty] | M,E |  | 5200 acres | This project will provide long-term protection for Dungeness Spit and Dungeness Bay through the purchase of conservation easements and properties, and the relocation or decommission of structures and infrastructure along the entire Dungeness drift cell. |  |  |  | 2 |  |  | Dungeness Drift Cell Conservation
2+ | North Sequim Bay Drift Cell Conservation |  | 0 | [13 empty] | Conceptual | [7 empty] | M,E |  | 269 acres | Permanent protection will be provided for Gibson, South, Travis and Paradise Cove Spits, all clustered near the entrances to WA Harbor and Sequim Bay, along with the 5.2 miles of coastal feeder bluffs that support the spits. |  |  |  | 2,3 |  |  | North Sequim Bay Drift Cell Conservation
2 | Washington Harbor Habitat Restoration | JSKT | 1800000 | 0 | 1800000 | ESRP, SRFB, PSAR | [10 empty] | Complete Construction | 1800000 | [6 empty] | M,E |  | 37 acres | Complete funded construction project to replace sewer line and bridge with new facilities to provide for fish passage and habitat forming processes. |  |  |  | 2, 7 |  |  | Washington Harbor Habitat Restoration
2 | Washington Harbor Habitat Protection Project |  | 0 | [13 empty] | Feasibility Pending | [7 empty] | M,E |  | 75 acres | This habitat protection project will purchase conservation easements to permanently protect a 150 to 450-foot wide riparian buffer (approximately 75 acres) surrounding Washington Harbor. The bed of Washington Harbor is state-owned. |  |  |  | 2 |  |  | Washington Harbor Habitat Protection Project
2+ | Meadowbrook Creek and Dungeness River Reconnection | NOSC | 0 |  |  | PSAR, Donations | [10 empty] | Feasibility Completed, Design Completed | [7 empty] | E,M,R |  | 5000 ft | This project aims to improve access to valuable estuarine and off-channel habitat by enhancing and stabilizing the connection between Meadowbrook Creek and the mainstem of the Dungeness River. |  |  |  | 1,3,5 |  |  | Meadowbrook Creek and Dungeness River Reconnection
2+ | Gray’s Marsh Restoration and Feasibility Design Phase 1 | WDFW | 0 |  |  | SRFB | [10 empty] | Conceptual | [7 empty] | E,R |  | 140 acres | Graysmarsh is an approximately 140-acre freshwater/brackish water marsh located at the mouth of Gierin Creek (WRIA 18.), which enters the Strait of Juan de Fuca immediately east of Dungeness Bay. The landowners are interested in learning what the available restoration alternatives are. |  |  |  | 2,3 |  |  | Gray’s Marsh Restoration and Feasibility Design Phase 1
2 | Three Crabs Nearshore and Estuarine Restoration | NOSC | 50000 |  |  | SRFB, ESRP | [10 empty] | preliminary design | 50000 | [6 empty] | E,M,R,W |  | 40 acres | Removal of infrastructure,armor,fill, roadway from nearshore and estuary to allow restore of estuarine processes. restore ~5 acres of historic estuarine wetlands, reconnection of floodplain wetlands to improve habitat connectivity between 40 Acres of wetlands |  |  |  | 2,5,7 |  |  | Three Crabs Nearshore and Estuarine Restoration
|  |  | 1850000 | [14 empty] | 1850000 |  | 0 |  | 0
Regional |  |  | 0
1,2,3, or 4 | Derelict Gear Removal | HCSEG, NWSF | 300000 | 300000 | 0 | NOAA, private foundation, ESRP | Inventory | ? | Remove and Inventory | ? | Remove and Inventory | ? | Remove and Inventory | ? | Remove and Inventory | ? | Inventory and remove | 100000 | Inventory and remove | 100000 | Inventory and remove | 100000 |  |  | E,M | Marine | ? | Inventory marine subtidal areas of Hood Canal for derelict nets and pots and continue removal process |  |  |  | 2 | 18-05 |  | Derelict Gear Removal
1, 2 or 3 | Regional Riparian Successional Strategy | Multiple | 900000 | 600000 | 300000 | SRFB, Noxious weed boards, partner in-kind, DNR |  |  | Survey and inventory noxious weeds | 75000 | Survey, inventory, remove noxious weeds; begin riparian assessment | 300000 | Survey, inventory, remove noxious weeds; implement riparian plantings | 300000 | Survey, inventory, remove noxious weeds; implement riparian plantings | 300000 | Survey, inventory, remove noxious weeds; implement riparian plantings | 300000 | Survey, inventory, remove noxious weeds; implement riparian plantings | 300000 | Survey, inventory, remove noxious weeds; implement riparian plantings | 300000 |  |  | R | All except marine | ? | Survey, inventory, and control exotic, invasive vegetation species along high priority freshwater reaches; prepare sites, plant, and maintain sites following recommendations from riparian assessment. |  |  |  | 1,3,5 | 18-03, | Level Two Riparian for all Chum & Chinook watersheds | Regional Riparian Successional Strategy
1 or 2 | Summer Chum and Chinook Riparian Conservation/Acquisition | Multiple | 900000 | 600000 | 300000 | SRFB, PSAR, WWRP, Coastal Wetlands |  | 0 |  | 75000 |  | 300000 |  | 300000 |  | 300000 | community outreach, appraisals, transactions | 300000 | community outreach, appraisals, transactions | 300000 | community outreach, appraisals, transactions | 300000 |  |  | L | All | ? | Working with volunteer landowners, develop high priority land acquisitions that either protect high quality habitats at risk of conversion or impacted habitats which require restoration that is incompatible with current land uses or landowner desires. |  |  |  | 1,2,3,4,5,6,7 |  | Level Two Conservation for all Chum & Chinook watersheds | Summer Chum and Chinook Riparian Conservation/Acquisition
1,2,3 or 3 | Hood Canal Nearshore Prioritization Tool | Kitsap Co DCD | 234277 |  | 0 | [11 empty] | planning | 234277 | [9 empty] | This project will address existing data sets and methodologies to develop a prioritized list of actions for nearshore habitat restoration and protection, for the Hood Canal and Eastern Strain of Juan de Fuca | Identified as a gap; Ranked #3 in Hood Canal prioritized actions list |  |  |  | PA 01-03-005 |  | Hood Canal Nearshore Prioritization Tool
1,2,3 or 4 | Hood Canal S Chum Nearshore Habitat Use Assessment (Nearshore Science Gap) | WFC, PGST, DFW, others? | 504840 |  | 0 | SRFB, PSAR, NOAA, WDFW | [10 empty] | Implement Phase 2 | 284840 | Implement phase 3 | 220000 |  |  |  |  | E,M | Marine | ? | Project will quantify nearshore habitat usage by ESA listed Hood Canal Summer Chum throughout the ESU in order to better prioritize nearshore habitat restoration and protection projects | Identified as a gap; Ranked #2 in Hood Canal prioritized actions list |  |  | 2 | PA 01-03-004 |  | Hood Canal Summer Chum Nearshore Habitat Use Assessment
|  |  | 2839117 | [14 empty] | 1219117 |  | 920000 |  | 700000
Hatchery Capital Projects |  |  | 0
1 | Mid-Hood Canal Conservation Hatchery Plan | LLTK, Tribes, DFW, HCCC | 269562 | 92205 | 177357 | [11 empty] | Implement SOW | 177357 | Implement SOW | 92205 | [7 empty] | Assess genetic heritage of Chinook within the Dosewallips, investigate potential chinook stocks given context, develop recommendations for stock reintroduction; incorporate into RITT Common Framework |  |  |  |  | Not in HWS |  | Mid-Hood Canal Conservation Hatchery Plan
1 | Skokomish Hatchery Facilities, per Cushman License | Skokomish, TP | #VALUE! | ? | ? | [11 empty] | Hatchery construction | ? | Hatchery construction/operation | ? | Operations | ? | [5 empty] | Capital facilities necessary for chinook supplementation, via Cushman FERC license and settlement agreement |  |  |  |  | Not in HWS |  | Skokomish Hatchery Facilities, per Cushman License
1 | Lakes Cushman and Kokanee passage down/upstream | Tacoma Power | #VALUE! | 0 | ? | TP | settlement talks |  | settlement talks |  | agreement |  | FERC License and design |  |  |  | adult & juvenile passage construction | ? | monitoring | ? |  |  |  |  | P | Mainstem | Remediate fish barrier | Create upstream (trap) and downstream (floating surface collector) passage past Cushman Project, including fish handling/sorting facility |  |  |  | 7 | Not in HWS |  | Lakes Cushman and Kokanee passage down/upstream
| Could look at adding chum capture facilities (start with Crawford assessment)? |  | 0
|  |  | 269562 | [14 empty] | 177357 |  | 92205 |  | 0
TOTAL CAPITAL NEED: |  |  | 78766335 | 61561059 | 17332616 |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 15082051 |  | 37399884 |  | 26284400

## Category Keys
Keys to the categories of projects laid out in spread sheet columns:
Habitat Limiting Factors
1 - Degraded floodplain and in-river channel structure
2 - Degraded nearshore and estuarine conditions and loss of associated habitat
3 - Riparian area degradation and loss of in-river large woody debris
4 - Excessive sediments in spawning gravels
5 - Degraded water quality and temperature
6 - Impaired instream flows
7 - Barriers to fish passage
For Habitat Projects:
Acquisition
(note: If the project’s scope includes just acquisition, with future restoration planned as part of a subsequent phase, list AR. If the project’s scope includes both purchase and restoration, list both AR and R.)
AP- Acquisition for protection
AR-Acquisition for restoration
R -Restoration
Restoration Type & Performance
I - Instream habitat projects (stream miles treated)
W - Wetland habitat projects (acres created/treated)
E - Estuarine habitat projects (acres created and treated)
L - Land acquisition projects (acres/ miles acquired for protection and/or restoration)
R - Riparian habitat projects (stream miles/acres treated)
U - Upland habitat projects (acres treated)
P - Fish passage projects (barriers removed/stream miles opened/fish screens installed)
M - Marine shoreline projects (miles/acres) (pocket estuaries and shorelines outside of natal delta areas and tributaries to Puget Sound)
F - Floodplain reconnection projects (miles/acres)
Location w/in watershed
Marine shorelines (pocket estuaries and shorelines outside of natal delta areas and tributaries to Puget Sound)
Estuaries
Mainstem
Tributaries (all tributaries to mainstem rivers)
Headwaters